## Software Development
Type | Status | Title | Start date | End date | Duration (in days) | % Complete
Task |  | Research music teaching techniques | 2019-01-20 | 2019-02-01 | 10 | 5
Task |  | Research best filaments (LEDs?) to print | 2019-01-25 | 2019-02-07 | 10 | 10
Task |  | Research micro controller | 2019-01-27 | 2019-02-08 | 10 | 15
Task |  | Choose best technologies to use (IDE,language etc) | 2019-01-28 | 2019-02-08 | 10 | 20
Task |  | Research blue tooth (is it reasonable?) | 2019-01-30 | 2019-02-12 | 10 | 25
Task |  | Data structure for file | 2019-02-10 | 2019-02-22 | 10 | 30
Task |  | Make sounds for the application | 2019-02-15 | 2019-02-28 | 10 | 35
Task |  | Make 3D model | 2019-02-20 | 2019-03-05 | 10 | 40
Task |  | Print 3D model | 2019-02-28 | 2019-03-13 | 10 | 45
Task |  | Parsed serialized input so they become usable | 2019-03-08 | 2019-03-21 | 10 | 50
Task |  | Design main menu | 2019-03-10 | 2019-03-22 | 10 | 55
Task |  | Design UI interaction elements | 2019-03-12 | 2019-03-25 | 10 | 60
Task |  | Convert micro controller output to note value | 2019-03-15 | 2019-03-28 | 10 | 65
Task |  | Implement saving and loading | 2019-03-17 | 2019-03-29 | 10 | 70
Task |  | Graphics creation | 2019-03-20 | 2019-04-02 | 10 | 75
Task |  | Create visual interface | 2019-03-21 | 2019-04-03 | 10 | 80
Task |  | Come up with interface that is interacted with | 2019-03-28 | 2019-04-10 | 10 | 85
Task |  | Throw together small tutorial | 2019-03-28 | 2019-04-10 | 10 | 90
Task |  | Find little kids for testing | 2019-04-02 | 2019-04-15 | 10 | 100