## Software Development
Type | Status | Title | Start date | End date | Duration (in days) | % Complete | Primary Person | Hours
Task |  | Research music teaching techniques | 2019-01-20 | 2019-02-01 | 10 | 5 | Adam Tait | 13
Task |  | Research best filaments (LEDs?) to print | 2019-01-25 | 2019-02-07 | 10 | 10 | Eric Gatto
Task |  | Choose best technologies to use (IDE,language etc) | 2019-01-28 | 2019-02-08 | 10 | 15 | Jason Judis
Task |  | Research micro controller | 2019-01-27 | 2019-02-08 | 10 | 20 | John Rose
Task |  | Research blue tooth (is it reasonable?) | 2019-01-30 | 2019-02-12 | 10 | 25 | John Rose
Task |  | Create data structure for file | 2019-02-10 | 2019-02-22 | 10 | 30 | Eric Gatto
Task |  | Make sounds for the application | 2019-02-15 | 2019-02-28 | 10 | 35 | Adam Tait | 12
Task |  | Make 3D model | 2019-02-20 | 2019-03-05 | 10 | 40 | Eric Gatto
Task |  | Print 3D model | 2019-02-28 | 2019-03-13 | 10 | 45 | Eric Gatto
Task |  | Parsed serialized input so they become usable | 2019-03-08 | 2019-03-21 | 10 | 50 | John Rose
Task |  | Convert micro controller output to note value | 2019-03-15 | 2019-03-28 | 10 | 55 | John Rose
Task |  | Come up with interface that is interacted with | 2019-03-28 | 2019-04-10 | 10 | 60 | Adam Tait
Task |  | Graphics creation (1) | 2019-03-20 | 2019-04-02 | 10 | 65 | Eric Gatto
Task |  | Graphics creation (2) | 2019-03-20 | 2019-04-02 | 10 | 70 | Adam Tait | 10
Task |  | Design UI interaction elements | 2019-03-12 | 2019-03-25 | 10 | 75 | Jason Judis
Task |  | Design main menu | 2019-03-10 | 2019-03-22 | 10 | 80 | Jason Judis
Task |  | Create visual interface | 2019-03-21 | 2019-04-03 | 10 | 85 | Adam Tait
Task |  | Implement saving and loading | 2019-03-17 | 2019-03-29 | 10 | 90 | John Rose
Task |  | Create application tutorial | 2019-03-28 | 2019-04-10 | 10 | 95 | Jason Judis
Task |  | Find children for testing | 2019-04-02 | 2019-04-15 | 10 | 100 | Jason Judis