## Software Development
Type | Title | Start date | End date | Duration (in days) | % Complete | Primary Person | Adam | Eric | Jason | John
| Fall Hours | [5 empty] | 56.5 | 52 | 51 | 56
Task | Research music teaching techniques | 2020-01-20 | 2020-02-01 | 10 | 5 | Adam Tait | 13
Task | Research best filaments (LEDs [Y]) to print | 2020-01-25 | 2020-02-07 | 10 | 10 | Eric Gatto |  | 8 |  | 5
Task | Choose best technologies to use (IDE,language etc) | 2020-01-28 | 2020-02-08 | 10 | 15 | Jason Judis |  |  | 5
Task | Research micro controller | 2020-01-27 | 2020-02-08 | 10 | 20 | John Rose |  |  |  | 23
Task | Research blue tooth (is it reasonable [N]) | 2020-01-30 | 2020-02-12 | 10 | 25 | John Rose |  |  |  | 10
Task | Create data structure for file | 2020-02-10 | 2020-02-22 | 10 | 30 | Eric Gatto | 3 | 5 |  | 3
Task | Make sounds for the application | 2020-02-15 | 2020-02-28 | 10 | 35 | Adam Tait | 14 | 2
Task | Make 3D model | 2020-02-20 | 2020-03-05 | 10 | 40 | Eric Gatto |  | 22
Task | Print 3D model | 2020-02-28 | 2020-03-13 | 10 | 45 | Eric Gatto |  | 37
Task | Parsed serialized input so they become usable | 2020-03-08 | 2020-03-21 | 10 | 50 | John Rose | 2 |  |  | 32
Task | Convert micro controller output to note value | 2020-03-15 | 2020-03-28 | 10 | 55 | John Rose | 1 |  |  | 9
Task | Come up with interface that is interacted with | 2020-03-28 | 2020-04-10 | 10 | 60 | Adam Tait | 17 | 3 | 9
Task | Graphics creation (1) | 2020-03-20 | 2020-04-02 | 10 | 65 | Eric Gatto | 2 | 5
Task | Graphics creation (2) | 2020-03-20 | 2020-04-02 | 10 | 70 | Adam Tait | 10 | 3
Task | Design UI interaction elements | 2020-03-12 | 2020-03-25 | 10 | 75 | Jason Judis | 8 |  | 10
Task | Design main menu | 2020-03-10 | 2020-03-22 | 10 | 80 | Jason Judis | 2 |  | 28
Task | Create visual interface | 2020-03-21 | 2020-04-03 | 10 | 85 | Adam Tait | 17 |  | 17
Task | Implement saving and loading | 2020-03-17 | 2020-03-29 | 10 | 90 | John Rose | 16 | 16 | 2 | 16
Task | Create application tutorial | 2020-03-28 | 2020-04-10 | 10 | 95 | Jason Judis | 4 | 2 | 22 | 2
Task | Testing and Documentation | 2020-04-02 | 2020-04-15 | 10 | 100 | Everyone | 18 | 10 | 8 | 8
HOURS
[6 empty] | Fall Hours | 56.5 | 52 | 51 | 56
[6 empty] | Spring Hours | 127 | 113 | 101 | 108
[6 empty] | Total Hours | 183.5 | 165 | 152 | 164